## 3 Options
Option 1 - Leveraging onsite
Sl No | Role | Location | People Identified | Duration In Weeks | Hours | Bill Rate | Cost
1 | Consultant | Onsite | David Lazar | 15 | 315 | 180 | 56700 | Points to note:
2 | Consultant | Onsite | Dave Chema | 9 | 189 | 180 | 34020 | David and Dave - 0.5 FTE each
2 | Micro Services Architect | Onsite | TBD | 15 | 630 | 100 | 63000 | Increased client/dev team interaction
3 | Technical Product Owner | Onsite | Senthil | 15 | 630 | 65 | 40950 | 80% of current insight team is available for Insight work
4 | Software Dev Engineer -1 | Onsite | Shameer | 15 | 630 | 60 | 37800 | Reduced Billing of InSight | 78750
5 | Software Dev Engineer -2 | Offshore | TBD | 15 | 630 | 18 | 11340 | Actual Revenue | 205300
6 | Software Dev Engineer -3 | Offshore | TBD | 15 | 630 | 18 | 11340
7 | QA Engineer -1 | Offshore | TBD | 15 | 630 | 15 | 9450
8 | QA Engineer -2 | Offshore | TBD | 15 | 630 | 15 | 9450
| Travel Costs (billed on actuals) | [5 empty] | 10000
284050
Option 2 - Leveraging Insight team
Sl No | Role | Location | People Identified | Duration In Weeks | Hours | Bill Rate | Cost | Points to note:
1 | Advisory Consultant |  | David Lazar | 15 | 94.5 | 180 | 17010 | This option maximises use of current team
2 | Advisory Consultant |  | Dave Cheema | 9 | 56.7 | 180 | 10206 | Team builds and retain knowledge of microservices philosophy
3 | Micro Services Architect | Onsite | George / Gireesh (50% each) | 6 | 252 | 80 | 20160 | Only 50% of current Insight team is available for regular Insight work
4 | Micro Services Architect | Offshore | George / Gireesh (50% each) | 9 | 378 | 30 | 11340 | Reduced Billing of InSight
5 | Technical Product Owner | Onsite | Senthil | 15 | 630 | 65 | 40950 | Sanjay Offshore cost | 9450
6 | Software Dev Engineer -1 | Onsite | Shameer | 15 | 630 | 60 | 37800 | George Offshore cost | 13230
7 | Software Dev Engineer -2 | Onsite | Sanjay | 15 | 630 | 65 | 40950 | Shameer Onsite cost | 37800
8 | Software Dev Engineer -3 | Offshore | TBD | 15 | 630 | 18 | 11340 | Senthil Onsite cost | 40950
9 | QA Engineer -1 | Onsite | TBD | 15 | 630 | 65 | 40950 | Total | 101430
10 | QA Engineer -2 | Offshore | TBD | 15 | 630 | 15 | 9450
| Travel Costs (billed on actuals) | [5 empty] | 10000 | Actual Revenue | 148726
| Miscellaneous Expense | [5 empty] | 7000
250156
Option 3 - Leveraging offshore
Sl No | Role | Location | People Identified | Duration In Weeks | Hours | Bill Rate | Cost
1 | Consultant | Onsite | David Lazar | 15 | 315 | 180 | 56700 | Points to note:
2 | Consultant | Onsite | Dave Chema | 9 | 189 | 180 | 34020 | David and Dave - 0.5 FTE each
2 | Micro Services Architect | Offshore | Gireesh | 15 | 630 | 40 | 25200 | Increased client/user interaction
3 | Technical Product Owner | Onsite | Senthil | 15 | 630 | 65 | 40950 | 80% of current Insight team is available for regular Insight work
4 | Software Dev Engineer -1 | Offshore | Sanjay | 15 | 630 | 18 | 11340 | Reduced Billing of InSight | 40950
5 | Software Dev Engineer -2 | Offshore | TBD | 15 | 630 | 18 | 11340 | Actual Revenue | 178840
6 | Software Dev Engineer -3 | Offshore | TBD | 15 | 630 | 18 | 11340
7 | QA Engineer -1 | Offshore | TBD | 15 | 630 | 15 | 9450
8 | QA Engineer -2 | Offshore | TBD | 15 | 630 | 15 | 9450
| Travel Costs (billed on actuals) | [5 empty] | 10000
219790

## temp
Assumptions
| Architect Cost | 100 dollars / hr | instead of 180 / hr
| Consultants | .5 FTE and Dave for 9 weeks
| Sprint Duration | 3 weeks
| Hours per sprint | 42 (167 /4)
| Total Sprints | 5
Onsite Driven Model
Sl No | Role | Location | People Identified | Duration In Weeks | Hours | Bill Rate | Cost | Column1
1 | Consultant | Onsite | David Lazar | 15 | 315 | 180 | 56700
2 | Consultant | Onsite | David Chema | 9 | 189 | 150 | 28350
2 | Micro Services Architect | Offshore | MS Architect | 15 | 630 | 40 | 25200
3 | Technical Product Owner | Onsite | Senthil | 15 | 630 | 65 | 40950
4 | Software Dev Engineer -1 | Onsite | Shameer | 15 | 630 | 65 | 40950
5 | Software Dev Engineer -2 | Offshore | TBD | 15 | 630 | 18 | 11340
6 | Software Dev Engineer -3 | Offshore | TBD | 12 | 504 | 18 | 9072
7 | QA Engineer -1 | Offshore | TBD | 15 | 630 | 15 | 9450
8 | QA Engineer -2 | Offshore | TBD | 15 | 630 | 15 | 9450
| Travel Costs | [5 empty] | 10000
241462

## Matrix of options
| Intial turn around time | Application Knowledge | Technical Expertise | Onboarding Time | Additional Cost after reducing InSight | Impact to InSight Development
|  | Learning Curve | Learning Curve
Leveraging Onsite | Quick | Yes | No | 1 to 2 months | 205300 | Medium
Leveraging Insight team (Offshore and Onsite) | Delayed | No | Yes, minimal | 0 | 131510 | Need to reduce the development work on InSight
Leveraging Offshore | Delayed | Yes | No | 1 to 2 months | 179940 | Minimal